## Product Backlog
ID (User Story) | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Implement Sign-In Feature | In order to provide securtity user require to have sign-in feature | High | 5 | 0 | 0 | New
2 | Implement Dashboard | Doctor want to see the overview of upcomming meetings and patients... | Mid | 8 | 0 | 0 | New
3 | Implement Cases | Doctor may consolidate all data inside a Case. The case includes the history all visits and all changes made | Mid | 12 | 0 | 0 | New
Total |  |  |  | 25 | 0 | 0

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | GIT Name | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | User Model | Design user database entry | Database | Tobias | Smubs | Nalet | High | 1 |  |  | New
1.2 | 1 | Sign-In View | Define HTML template for Sign-In | UI | Nalet | nalet | Sergii | High | 1 |  |  | New
1.3 | 1 | Define Sign-In Controller | Write Controller that will check if user credentials are valid | Controller | Sergii | dexterite | Michael | High | 2 |  |  | New
1.4 | 1 | Define Midleware for Login | Define middleware class that will check if user is signed-in | UI | Sergii | dexterite | Michael | High | 1 |  |  | New
2.1 | 2 | Patient Model | Design patient database entry | Database | Tobias | Smubs | Nalet | Mid | 1 |  |  | New
2.2 | 2 | Appointments Model | Design appointments database entry | Database | Tobias | Smubs | Nalet | Mid | 1 |  |  | New
2.3 | 2 | Define overal html template | Define header ¦ content ¦ footer templates in HTML for VAADIN | UI | Nalet | nalet | Tobias | High | 2 |  |  | New
2.4 | 2 | Define dashboard template | Define HTML template for Dashboard | UI | Nalet | nalet | Reto | Mid | 2 |  |  | New
2.5 | 2 | Define dashboard controller | Define controller that will consolidate data from the model and put into the view | Controller | Sergii | dexterite | Michael | High | 1 |  |  | New
2.6 | 2 | Define Dashboard data queries in the models | Take Patient and Appointments Model and define all necessary data retrievals | Database, Model | Sergii | dexterite | Michael | High | 1 |  |  | New
3.1 | 3 | DB Design + Case Model | Create a case Model and make design for DB | Database, Model | Tobias | Smubs | Reto | Mid | 2 |  |  | New
3.2 | 3 | Case Controller + Define data queries |  | Controller, Model | Michael | michaelraess | Tobias | Mid | 5 |  |  | New
3.3 | 3 | Design Case View |  | UI | Reto | retozoss | Sergii | Mid | 5 |  |  | New
3.4 | 3 |  |  |  |  | #N/A

## Scrum Time
Names | Total Time | GIT Names
Sergii | 5 | dexterite
Tobias | 5 | Smubs
Nalet | 5 | nalet
Reto | 5 | retozoss
Michael | 5 | michaelraess